## Sheet1
Project Phases For Infernos
Day1 | Documentation | Done
Day1 | Report | Done
Day1 | Design | Done
Day1 | Architecture | Done
Day2 | Modelling | Pending
Day2 | Sensor Testing & Caliberation | Pending
Day3 | Model Implementation | Pending
Day3 | Circuitry | Pending
Day3 | Testing | Pending
Day4 | Final Code | Pending
Day4 | Compiling Circuitry with Final model | Pending
Day5 | Final Test and Caliberations | Pending
Day5 | Submission | Pending